| Student Support Leadership Initiative (SSLI) 2011-12Mid Year Report BackTemplate |  |  |  |  |
| --- | --- | --- | --- | --- |
| . |  |  |  |  |
| Date: December 16th, 2011 Cluster No.: 17 Cluster Lead Board Contact Information: |  |  |  |  |
| Name: |  | Donaleen Hawes, Superintendent of School Effectiveness |  |  |
| Email Address: |  | Donaleen.Hawes@cdsbeo.on.ca |  |  |
| Phone Number: REPORTING QUESTIONS: |  | 613 283-5007 X234 |  |  |
| 1. | Please outline the progress you have made to date based on your 2011-2012 Cluster Plan. Please also outline the performance measures you are using to monitor your ongoing performance. |  |  |  |
| Key Deliverables |  |  | Progress to Date |  |
| Extended Pilotson Coordinated Services |  |  | Xxxxx - The pilot project introduced last year has been extended and are in the process of expanding. $10 000 Performance Measures - Extension and expansion of pilots introduced last year - Leeds Grenville pilot to support Transition to School Initiative in Gananoque |  |
| Community VTRA Training and Coordination |  |  | - Additional training for the team of Train the Trainers are in the process of planning and delivering Level 1 training - Agency and School Board staff are being given Level 2 training. Performance Measures $10 000 - Agency and school board staff trained/or planned to be trained |  |
| Integrated and Aligned Service Model identified visually looking at the Algoma Model |  |  | - Board and agency intervention supports and therapeutic services have been identified. - Posters and inserts for student agendas will be prepared. $10 000 Performance Measures - Services identified - Accompanying resources developed and distributed (eg. Posters and inserts for student agendas, poster for agency staff) |  |
| Suicide Protocol |  |  | - Steering Committee is being established based on the work in Lanark County. $10 000 - Protocol development involving School Boards and keyCommunity Agencies. Performance Measures - Steering Committee formed - Protocol developed and early implementation |  |
| Checkered Flags Training and Implementation |  |  | - Continue training and full implementation with schools and agencies 10 000 Performance Measures - All Schools and Agencies will be trained to use the document - Changes/ additions to document - , website - Translation of document into French - Registration of Domain name |  |
| Regional Celebration of SSLI Initiatives and Community Collaboration |  |  | - A plan is being developed to hold four regional forums. - Agency and school teams will be invited to participate $46 000 go back to regional groups – about building sustainability Culture of working together Connecting the dots |  |
| 2. | Please outline the expenditures the Cluster has made to date and details about how they support the Cluster plan. |  |  |  |
| Expenditure |  |  | Details | Amount |
| Expanded Pilot on Coordinated Services |  |  | - Funding has been provided to Open Doors to extend and expand the school based pilot | $10,000 |
| Community VTRA Training and Coordination |  |  | - Twenty five agency/school board staff trained for Level 2 - A team of trainers will deliver Level 1 training | $ 5,000 |
| Total Amount Spent to Date |  |  |  | $15,000 |